KSIA Regional Infrastructure

Decision Intelligence Platform

Business Requirements Document for Proof-of-Concept Implementation

Audience: EY internal product, design, data and engineering team

Implementation method: Interactive web POC supported by representative, clearly identified sample data

Visual references: Approved illustrative screen images to be attached alongside the corresponding sections

Core proposition

Committee decision intelligence, not project reporting The platform shall give the Regional Infrastructure Committee an integrated view of infrastructure readiness across and beyond KSIA boundaries, connecting airport assets and milestone dates to demand, supply, external-entity projects, interim and permanent solutions, funding, land, approvals, dependencies and required committee actions.

# 1. Business Context and Purpose

King Salman International Airport is being developed as an airport city and aerotropolis, comprising aviation assets, terminals, runways, cargo and logistics, private aviation, commercial and retail districts, hospitality, supporting developments and associated regional infrastructure. Much of the infrastructure enabling KSIA will be planned or delivered by external governmental entities, utility providers and other stakeholders beyond the KSIA boundary.

The Regional Infrastructure Committee requires a single decision-intelligence environment to maintain visibility of infrastructure works, entity commitments and prerequisites; assess whether the required infrastructure capacity will be operational by each KSIA milestone; identify gaps and dependencies; and support timely decisions, escalations and interventions.

## 1.1 Business questions the POC must answer

- Which KSIA assets and milestones are infrastructure-ready, at risk, conditional or blocked?

- What infrastructure demand is required by each asset and date?

- What existing, committed, planned and interim supply will be available?

- What gaps remain, during which periods, and which assets are affected?

- Which permanent or interim solutions can close each gap?

- Which external projects and entities are critical to KSIA readiness?

- Are funding, land, utility corridors, permits, approvals and procurement prerequisites secured?

- What is the integrated critical path to each asset or operational milestone?

- What changes under alternative growth, funding, delivery and land-availability scenarios?

- What decisions and interventions should the Committee prioritize?

## 1.2 Core readiness principle

Infrastructure readiness rule A KSIA asset shall be considered infrastructure-ready only when the required service capacity is forecast to be operational, connected and available at the required location by the asset’s required operational date, with critical prerequisites and interfaces completed. Project progress alone shall not determine readiness.

# 2. POC Scope and Screen Architecture

| # | Screen / capability | Purpose |
| --- | --- | --- |
| 0 | Landing Page | Executive infrastructure enablement overview, airport-city visual, workstream readiness, milestones, committee actions, prerequisites, entity performance and module navigation. |
| A | Executive Overview / Airport Visual | Interactive airport-city view showing regional infrastructure networks converging into KSIA and key-asset readiness. |
| 1 | Master Plan Readiness Cockpit | Readiness of KSIA assets, milestones and infrastructure workstreams. |
| 2 | Scenario Planning | Comparison of baseline and alternative futures and their readiness, funding and delivery impacts. |
| 3 | Supply, Demand & Gap Management | Time-phased demand, available supply, gaps, project contributions and gap-closure actions. |
| 4 | Infrastructure Solutions & Gap Closure | Permanent, interim and alternative solutions for identified infrastructure gaps. |
| 5 | Funding, Budget Requests & Cash Flow | Funding requirements, approvals, sources, releases, spending and funding gaps. |
| 6 | Land, Corridors, Approvals & Prerequisites | Land acquisition, rights-of-way, approvals, procurement and other enabling prerequisites. |
| 7 | Integrated Dependencies & Critical Path | Critical path from enabling infrastructure and external projects to every KSIA asset milestone. |
| 8 | AI Insights & Recommendations | Prioritized findings, root causes, interventions and decision recommendations. |
| Utility | Ask KSIA Assistant | Conversational access to governed platform data, shown beside the funding executive indicator. |

# 3. Common Platform Requirements

| ID | Business requirement | Priority |
| --- | --- | --- |
| CP-01 | Use a mixed EY light-and-dark visual theme: white/light-grey canvas, dark charcoal header and selected dark intelligence panels, EY yellow for emphasis only, and crisp high-contrast typography. | Must |
| CP-02 | Provide global filters for Major Development, KSIA Area, Infrastructure Stream, External Entity and Time Horizon. | Must |
| CP-03 | Provide infrastructure-stream values: All Infrastructure; Mobility & Roads; Public Transport; Potable Water; Wastewater; Power & Energy; District Cooling; Digital & Telecommunications; Stormwater & Drainage; Waste & Environmental Services; and Natural Gas. | Must |
| CP-04 | Retain filter context when users navigate between the Landing Page and detailed screens. | Must |
| CP-05 | Use consistent readiness statuses: Ready, Conditional, At Risk, Blocked and Not Assessed. | Must |
| CP-06 | Use consistent project statuses: On Track, At Risk, Delayed, Blocked, Completed and Not Started. | Must |
| CP-07 | Clearly distinguish actual, forecast, committed, planned permanent, interim and simulated values. | Must |
| CP-08 | Provide drill-through from asset, project, workstream, entity, prerequisite and committee decision records. | Must |
| CP-09 | Use the approved KSIA airport-city image or master plan as the common spatial reference. | Must |
| CP-10 | Display the source or data-update timestamp on detailed screens. | Should |
| CP-11 | Use representative POC data and ensure that sample figures are configurable from a central data file rather than hard-coded in UI components. | Must |
| CP-12 | Provide reusable filters, cards, charts, status indicators, tables, slide-out detail panels and module navigation components. | Must |

# 4. Landing Page Requirements

| Item | Definition |
| --- | --- |
| Objective | Provide the Committee with a single executive view of KSIA infrastructure enablement and direct access to all detailed capabilities. |
| Primary users | Committee members, KSIA leadership, infrastructure coordination team and sector leads. |
| Primary outputs | Infrastructure readiness, key assets, regional networks, milestones, committee decisions, prerequisites, entity performance and module navigation. |

ILLUSTRATIVE SCREEN REFERENCE Attach approved final Landing Page image.

## 4.1 Page composition

| ID | Business requirement | Priority |
| --- | --- | --- |
| LP-01 | Display a dark EY header with platform title, global filters, notifications, help and user controls. | Must |
| LP-02 | Display a large KSIA airport-city hero image with an Executive Overview action in the upper-left section. | Must |
| LP-03 | Display executive indicators for Overall Readiness, Assets Enabled, Assets at Risk, Assets Blocked, Critical Decisions Requiring Action and Funding Gap. | Must |
| LP-04 | Display Ask KSIA Assistant immediately beside the Funding Gap indicator; Ask KSIA Assistant shall not appear as a bottom module card. | Must |
| LP-05 | Display Upcoming Key Milestones with milestone year/date, asset name and readiness status. | Must |
| LP-06 | Display four dark intelligence panels: Infrastructure Readiness by Stream, Committee Action Center, Prerequisite Readiness Overview and External Entity Performance. | Must |
| LP-07 | Display eight sequential module cards: 1 Master Plan Readiness Cockpit; 2 Scenario Planning; 3 Supply, Demand & Gap Management; 4 Infrastructure Solutions & Gap Closure; 5 Funding, Budget Requests & Cash Flow; 6 Land, Corridors, Approvals & Prerequisites; 7 Integrated Dependencies & Critical Path; 8 AI Insights & Recommendations. | Must |
| LP-08 | Each module card shall contain the module number, title, concise purpose, representative visual and Explore action. | Must |
| LP-09 | The Landing Page shall not include implementation phases, Quick Access, a separate GIS module card or an external-project-progress module card. | Must |

## 4.2 Executive intelligence panels

| ID | Business requirement | Priority |
| --- | --- | --- |
| LP-10 | Infrastructure Readiness by Stream shall show each stream’s readiness percentage and status. | Must |
| LP-11 | Committee Action Center shall show action, severity, due date and access to all actions. | Must |
| LP-12 | Prerequisite Readiness shall show funding, land acquisition, permits and approvals, procurement readiness, utility corridors / rights-of-way and entity commitments. | Must |
| LP-13 | External Entity Performance shall show entity, project count and counts of on-track, at-risk and delayed projects. | Must |

# 5. Executive Overview and Airport-City Infrastructure View

| Item | Definition |
| --- | --- |
| Objective | Present the airport city as the focal point of regional infrastructure networks and show the readiness of key KSIA assets. |
| Primary users | Committee members and leadership. |
| Primary outputs | Infrastructure convergence visual, asset readiness, workstream filters, external project connections and regional constraints. |

ILLUSTRATIVE SCREEN REFERENCE Attach approved airport-city / infrastructure convergence image or map deep-dive image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| EO-01 | Display the beautified KSIA airport-city image as the dominant visual. | Must |
| EO-02 | Display regional infrastructure workstreams entering KSIA through color-coded network corridors and connection points. | Must |
| EO-03 | Display key asset markers for runways, terminals, Terminal 6, Airport City, cargo and logistics, MRO facilities, private aviation, commercial and retail, hospitality and other configured assets. | Must |
| EO-04 | Display readiness status using colored dots or rings directly beside the asset labels. | Must |
| EO-05 | Allow All Infrastructure or one infrastructure workstream to be selected; non-selected networks shall be visually de-emphasized. | Must |
| EO-06 | Selecting an asset shall reveal required infrastructure, linked external projects, responsible entities, required date, prerequisites and current readiness. | Must |
| EO-07 | Selecting an external network or project shall highlight the KSIA assets and milestones served. | Must |

# 6. Module 1 — Master Plan Readiness Cockpit

| Item | Definition |
| --- | --- |
| Objective | Assess whether KSIA assets and milestones are enabled by the required infrastructure services. |
| Primary users | Leadership, Committee members and infrastructure coordination team. |
| Primary outputs | Asset readiness, milestone readiness, workstream readiness, project risks and decisions required. |

ILLUSTRATIVE SCREEN REFERENCE Attach illustrative Master Plan Readiness Cockpit image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M1-01 | Display overall infrastructure readiness and counts of enabled, conditional, at-risk and blocked assets. | Must |
| M1-02 | Display readiness by key asset, milestone, infrastructure stream and external entity. | Must |
| M1-03 | For each asset, display required operational date, infrastructure streams at risk, critical external projects, funding/land constraints and next decision. | Must |
| M1-04 | Calculate readiness from capacity, timing, project delivery, prerequisites and interface readiness. | Must |
| M1-05 | Allow drill-through to Supply and Demand, Funding, Prerequisites, Dependencies and AI Insights. | Must |

# 7. Module 2 — Scenario Planning

| Item | Definition |
| --- | --- |
| Objective | Compare alternative infrastructure, growth, funding and delivery scenarios and their effects on KSIA readiness. |
| Primary users | Committee members, leadership, planners and infrastructure leads. |
| Primary outputs | Scenario comparison, readiness trends, asset impacts, funding impacts, spatial impacts, uncertainties and actions. |

ILLUSTRATIVE SCREEN REFERENCE Attach approved Scenario Planning image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M2-01 | Provide Baseline Plan, Accelerated Growth, Delayed Infrastructure, Funding Constrained and High Airport City Uptake scenarios. | Must |
| M2-02 | Allow configuration of passenger growth, cargo growth, Airport City development, external project delivery, funding availability, land availability, demand management and regulatory approvals. | Must |
| M2-03 | Compare overall readiness, assets at risk, passenger/cargo outcomes, total investment, funding gap, interim solutions and critical external projects. | Must |
| M2-04 | Display readiness trend over time for every scenario. | Must |
| M2-05 | Display readiness by key asset and a spatial impact preview. | Must |
| M2-06 | Display assumptions, key uncertainties, AI insights and recommended scenario actions. | Must |
| M2-07 | Allow a selected scenario to feed Modules 3, 4 and 7 while retaining Baseline as the approved reference. | Must |

# 8. Module 3 — Supply, Demand & Gap Management

| Item | Definition |
| --- | --- |
| Objective | Determine whether sufficient infrastructure supply will be available when each KSIA asset requires it and define the timing and magnitude of gaps. |
| Primary users | Infrastructure planners, sector leads, external-entity coordinators and Committee analysts. |
| Primary outputs | Demand profiles, supply sources, gap periods, project contributions, gap drivers and closure actions. |

ILLUSTRATIVE SCREEN REFERENCE Attach approved Supply, Demand & Gap Management image.

## 8.1 Infrastructure filters

| Infrastructure stream | Infrastructure types |
| --- | --- |
| Mobility & Roads | Regional roads, interchanges, internal roads, access corridors, parking and curbside. |
| Public Transport | Metro, rail, bus, shuttle and associated stations / depots. |
| Potable Water | Treatment plants, transmission pipelines, reservoirs, booster/pumping stations and distribution networks. |
| Wastewater | Collection networks, pumping stations, treatment plants, outfalls and reuse systems. |
| Power & Energy | Grid connections, bulk supply points, substations, transformers, transmission and distribution networks. |
| District Cooling | Cooling plants, thermal storage, transmission networks, distribution networks and energy transfer stations. |
| Digital & Telecommunications | Backbone fibre, ducts, exchanges, towers, small cells, data centres and operational ICT connections. |
| Stormwater & Drainage | Channels, culverts, retention/detention basins, pumping stations and outfalls. |
| Waste & Environmental | Waste handling, transfer, treatment, recycling and environmental-service facilities. |
| Natural Gas | City gates, pressure-reduction stations, pipelines and metering stations. |

## 8.2 Business requirements

| ID | Business requirement | Priority |
| --- | --- | --- |
| M3-01 | Provide filters for development/asset, infrastructure stream, infrastructure type, external entity and time horizon. | Must |
| M3-02 | Display required peak capacity, forecast available supply, remaining gap, gap period, gap status and confidence level. | Must |
| M3-03 | Plot time-phased demand and existing, committed, planned permanent, interim and total available supply. | Must |
| M3-04 | Display supply contribution by project at the asset’s required date and at project completion. | Must |
| M3-05 | Display requirement profile for construction, testing and commissioning, initial operations, ramp-up, full operations and ultimate build-out. | Must |
| M3-06 | Display key gap drivers including project delays, land, power, environmental approvals and other prerequisites. | Must |
| M3-07 | Display the gap-closure plan and required completion dates. | Must |
| M3-08 | Allow analysis by asset and by zone. | Must |

# 9. Module 4 — Infrastructure Solutions & Gap Closure

| Item | Definition |
| --- | --- |
| Objective | Identify and assess permanent, interim and alternative solutions that close confirmed supply or timing gaps. |
| Primary users | Infrastructure planners, sector leads, Committee analysts and decision-makers. |
| Primary outputs | Solution options, capacity contribution, cost, lead time, prerequisites, residual gap and recommended option. |

ILLUSTRATIVE SCREEN REFERENCE Attach illustrative Infrastructure Solutions & Gap Closure image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M4-01 | Create a gap record for each affected asset, stream, gap quantity, start date and end date. | Must |
| M4-02 | Support solution types: existing spare capacity, capacity reallocation, project acceleration, enhancement, new permanent project, interim solution, temporary arrangement, alternative connection, demand reduction and phased opening. | Must |
| M4-03 | For each option, display capacity contribution, service period, cost, delivery entity, lead time, funding, land, approvals, dependencies and delivery confidence. | Must |
| M4-04 | Display interim-to-permanent transition and decommissioning/repurposing assumptions. | Must |
| M4-05 | Compare solution options and identify recommended option, residual gap, required decision and latest decision date. | Must |
| M4-06 | Allow approved solutions to create or update project, funding, prerequisite and dependency records. | Must |

# 10. Module 5 — Funding, Budget Requests & Cash Flow

| Item | Definition |
| --- | --- |
| Objective | Track the funding required to deliver infrastructure projects and gap-closure solutions. |
| Primary users | Committee members, finance team, infrastructure leads and project owners. |
| Primary outputs | Funding position, requests, sources, approvals, releases, spending, cash flow and funding gaps. |

ILLUSTRATIVE SCREEN REFERENCE Attach illustrative Funding, Budget Requests & Cash Flow image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M5-01 | Display required, requested, approved, allocated, released, committed and spent values. | Must |
| M5-02 | Display funding gap by project, asset, infrastructure stream, entity and year. | Must |
| M5-03 | Support funding sources including KSIA, PIF, government allocation, utility provider, external entity, developer contribution, private-sector participation and other configured sources. | Must |
| M5-04 | Track funding-request status, amount, submission date, approval stage, decision owner, required date, forecast approval and conditions. | Must |
| M5-05 | Display planned versus actual cash flow and programs affected by funding constraints. | Must |
| M5-06 | Link each funding request to its projects, solutions, assets, milestones and committee decisions. | Must |

# 11. Module 6 — Land, Corridors, Approvals & Prerequisites

| Item | Definition |
| --- | --- |
| Objective | Monitor non-construction prerequisites that enable external infrastructure projects and KSIA connections. |
| Primary users | Committee members, land, legal, permitting, procurement and infrastructure teams. |
| Primary outputs | Land status, corridors, approvals, procurement readiness, commitments, blockers and affected assets/projects. |

ILLUSTRATIVE SCREEN REFERENCE Attach illustrative Land, Corridors, Approvals & Prerequisites image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M6-01 | Support prerequisite categories: land parcel, utility corridor, right-of-way, easement, access, staging area, permit, NOC, environmental approval, technical approval, procurement, utility diversion, external agreement and commissioning/handover requirement. | Must |
| M6-02 | Display total, available, in-progress, pending, at-risk and overdue prerequisites. | Must |
| M6-03 | For every prerequisite, track responsible entity, required date, forecast completion, status, evidence, blocker, next action and escalation. | Must |
| M6-04 | Display affected projects, assets and downstream milestones. | Must |
| M6-05 | Provide land and corridor mapping where coordinates are available. | Must |
| M6-06 | Highlight projects reported on track where a critical prerequisite is forecast late. | Must |

# 12. Module 7 — Integrated Dependencies & Critical Path

| Item | Definition |
| --- | --- |
| Objective | Show the complete critical path from enabling infrastructure through external projects, KSIA connections and enabling activities to every KSIA asset milestone. |
| Primary users | Committee members, schedulers, project controls, infrastructure leads and external-entity coordinators. |
| Primary outputs | Dependency network, critical path, forecast readiness date, delay impact, critical projects and interventions. |

ILLUSTRATIVE SCREEN REFERENCE Attach approved Integrated Dependencies & Critical Path image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M7-01 | Allow users to select a KSIA asset or milestone and display required date, forecast date, delay, criticality and overall path status. | Must |
| M7-02 | Model dependencies across enabling infrastructure, external projects, KSIA interfaces/connections, internal enablers and asset milestones. | Must |
| M7-03 | Distinguish critical, near-critical, non-critical and completed dependencies. | Must |
| M7-04 | Distinguish external dependencies, interface milestones and KSIA milestones. | Must |
| M7-05 | Display path length, total dependencies, external dependencies and driving projects. | Must |
| M7-06 | Calculate delay impact on the selected asset and downstream milestones. | Must |
| M7-07 | Display critical-path projects with entity, forecast finish, delay and criticality. | Must |
| M7-08 | Display recommended interventions and allow navigation to Funding, Prerequisites, Gap Closure or Committee Actions. | Must |

# 13. Module 8 — AI Insights & Recommendations

| Item | Definition |
| --- | --- |
| Objective | Surface material risks, opportunities, root causes and recommended committee interventions across the platform. |
| Primary users | Committee members, leadership and analysts. |
| Primary outputs | Prioritized insights, evidence, confidence, recommended actions and expected readiness impact. |

ILLUSTRATIVE SCREEN REFERENCE Attach illustrative AI Insights & Recommendations image.

| ID | Business requirement | Priority |
| --- | --- | --- |
| M8-01 | Generate findings across asset readiness, supply-demand gaps, project delivery, funding, prerequisites, dependencies and scenarios. | Must |
| M8-02 | For each insight, display affected asset, stream, project/entity, severity, confidence and supporting evidence. | Must |
| M8-03 | Provide root-cause analysis and show the contribution of identified drivers. | Must |
| M8-04 | Recommend interventions with expected readiness impact, cost, lead time, owner and latest action date. | Must |
| M8-05 | Allow approved recommendations to create committee actions or proposed solutions. | Must |
| M8-06 | Clearly label AI-generated content and distinguish evidence from inference. | Must |

# 14. Ask KSIA Assistant

| Item | Definition |
| --- | --- |
| Objective | Provide conversational access to trusted platform data and analysis without adding a separate module card. |
| Primary users | Committee members, leadership and analysts. |
| Primary outputs | Cited answers, generated visualizations, follow-up analysis and action handoffs. |

| ID | Business requirement | Priority |
| --- | --- | --- |
| AI-01 | Display Ask KSIA Assistant beside the Funding Gap executive indicator on the Landing Page. | Must |
| AI-02 | Answer questions using the active global-filter context. | Must |
| AI-03 | Cite the metric, dataset and source screen used for every substantive answer. | Must |
| AI-04 | Generate supporting charts, tables and airport-city visuals where applicable. | Must |
| AI-05 | Support follow-up questions and retain conversation history for the user session. | Must |
| AI-06 | Allow approved recommendations to be converted into actions, interventions or solution records. | Must |
| AI-07 | Apply guardrails against unsupported claims and label actual, forecast and simulated values. | Must |

# 15. Committee Action and Decision Model

| ID | Business requirement | Priority |
| --- | --- | --- |
| CM-01 | Track committee decision/action ID, title, category, severity, related asset, stream, project, entity and meeting date. | Must |
| CM-02 | Track direction, action owner, responsible entity, due date, status, evidence, latest update, escalation level and next decision. | Must |
| CM-03 | Use statuses: Pending, In Progress, Overdue, Closed and Superseded. | Must |
| CM-04 | Display pending and overdue actions on the Landing Page. | Must |
| CM-05 | Link actions directly to affected records and update related readiness views when resolved. | Must |

# 16. Core Data Model

| Entity | Minimum attributes |
| --- | --- |
| KSIA Asset / Milestone | ID, name, category, zone, required date, milestone type, status, criticality and parent development. |
| Infrastructure Requirement | Asset, stream, infrastructure type, demand profile, required capacity, required date, unit and confidence. |
| Supply Source | Stream, project/source, entity, type, capacity, allocated KSIA capacity, availability dates and confidence. |
| External Project | ID, name, entity, stream, infrastructure type, stage, baseline/forecast dates, progress, capacity contribution, risks and next milestone. |
| Gap | Asset, stream, quantity, unit, start/end dates, impact, status and residual exposure. |
| Solution | Gap, type, capacity contribution, cost, dates, entity, prerequisites, status and residual gap. |
| Funding Request | Project/solution, source, requested/approved/released amounts, status, dates, conditions and decision owner. |
| Prerequisite | Type, project/solution, entity, required/forecast dates, status, evidence, blocker and next action. |
| Dependency | Predecessor, successor, type, giving/receiving milestones, required/forecast dates, contingency and critical-path flag. |
| Committee Action | Decision/action, related records, owner, entity, due date, status, escalation and evidence. |
| Scenario | Name, assumptions, driver values, selected project delays, funding/land constraints, outputs and version. |
| AI Insight | Finding, severity, confidence, evidence, affected records, recommendation and action status. |

# 17. Calculation and Status Logic

| ID | Business requirement | Priority |
| --- | --- | --- |
| LG-01 | Supply gap = Required demand minus total available supply at the relevant date; total available supply includes existing, committed, planned capacity available by date and active interim supply. | Must |
| LG-02 | Asset readiness shall consider capacity sufficiency, supply availability date, external-project forecast, prerequisite readiness, KSIA interfaces and commissioning. | Must |
| LG-03 | Ready: sufficient operational supply is forecast before the required date and critical prerequisites are complete or on track with acceptable contingency. | Must |
| LG-04 | Conditional: sufficient supply is forecast by the required date but material prerequisites, interfaces or limited schedule contingency remain. | Must |
| LG-05 | At Risk: supply, project forecast or critical prerequisites may miss the required date. | Must |
| LG-06 | Blocked: a confirmed critical dependency/prerequisite prevents progression or no credible gap-closure solution exists. | Must |
| LG-07 | Critical path shall be the longest dependency chain determining the earliest forecast readiness date for the selected asset milestone. | Must |
| LG-08 | Scenario outputs shall be calculated separately and shall not overwrite the Baseline dataset. | Must |

# 18. Representative POC Dataset

The POC shall use a coherent sample dataset that demonstrates the complete decision journey while remaining configurable. The primary use case shall be Terminal 6 potable-water readiness.

| Dataset component | Representative content |
| --- | --- |
| KSIA assets | Terminal 6, Private Aviation, Airport City first asset, Iconic Terminal, Cargo Village, runways, MRO, commercial/retail and hospitality. |
| Infrastructure streams | All streams listed in CP-03, with detailed sample data for Potable Water, Power & Energy, Mobility & Roads, Digital & Telecommunications and District Cooling. |
| External entities | RCRC, NWC, SWA, SEC, CST, MOT, Riyadh Municipality and configurable additional entities. |
| Projects | At least 20 external projects with baseline/forecast dates, progress, capacity contribution, risks, prerequisites and affected assets. |
| Terminal 6 water case | Demand by Q3 2028; existing and committed supply; delayed permanent transmission pipeline; interim treatment solution; funding, land, power and environmental prerequisites. |
| Committee actions | At least 10 actions covering funding, land, approvals, project acceleration, corridor availability and interim solutions. |
| Scenarios | Baseline, Accelerated Growth, Delayed Infrastructure, Funding Constrained and High Airport City Uptake. |

# 19. POC Acceptance Criteria

| ID | Business requirement | Priority |
| --- | --- | --- |
| AC-01 | All screens open from the Landing Page and retain the selected global-filter context. | Must |
| AC-02 | The airport-city image, infrastructure convergence view, key assets and dark intelligence panels visually align with the approved illustrative images. | Must |
| AC-03 | The Landing Page contains the exact eight sequential module cards and Ask KSIA Assistant placement defined in LP-04 and LP-07. | Must |
| AC-04 | Changing asset, workstream or scenario updates all relevant KPIs, charts, tables and status indicators on the current screen. | Must |
| AC-05 | The Terminal 6 water storyline can be followed end-to-end from asset readiness to gap, project contributions, solution, prerequisites, critical path and recommendation. | Must |
| AC-06 | The user can select a KSIA milestone and view the integrated critical path and downstream impacts. | Must |
| AC-07 | Scenario results remain separate from Baseline and can be compared side by side. | Must |
| AC-08 | Every visualized number is sourced from the central POC data model and is not independently hard-coded in the UI. | Must |
| AC-09 | No unsupported real-world data shall be presented as factual; representative data shall remain clearly identifiable within the POC configuration. | Must |